BAKER TILLY AUDIT RECOMMENDATIONS 2013-15

and MAZARS 2015

Audit Recommendations for 2013-15

| Status |  | Internal Audit Report |  |  |  |  |  | Audit Report Date |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | BUSINESS CONTINUITY (Non IT) Follow up |  |  |  |  |  |  |  | 11 June 2014 |  |  |  |
|  |  | HIGH: 0 |  |  | MEDIUM: 0 |  |  |  |  | LOW: 1 |  |  |  |
|  |  | Low Recommendation 1.11b Restated recommendation - The Office of the Police and Crime Commissioner (OPCC) should ensure that dates are set for testing the Business Continuity Plan (BCP) to ensure that it is fit for purpose. Implementation Target Date: By the end of second quarter 2014 End of October 2015 Person Responsible: Angela Perry - OPCC Update May 2014: Acknowledged not yet completed – delays contributed to by changes in arrangements, stage 2 transfer work and 3 different CFO personnel in last year. Update 4th September 2014: The Business Continuity Plan is being revised and re-formatted into the Force template. A table top exercise is planned to take place before the end of the calendar year to test the Plan. A new temporary member of staff who has a background in risk and business continuity at a local authority is leading on the work - Angela Perry OPCC Update November 2014: The OPCC are still in the process of populating the templates. Deadline for the desktop exercise may be pushed back to January due to staff absences and Interviews taking place. Update January 2015: This is currently being take to the PCC SMT and therefore there will be an update for the next report. Update April 2015: The OPCC has a permanent member of staff in place now to lead on this area of business. The member of staff has previous knowledge and experience in this area. A table top exercise was undertaken on the 12th March 2015 and the OPCC’s BCP is currently being reviewed and updated to reflect the outcomes from the exercise. Senior Management Team (SMT) will review and agree the final version by June 2015. An action plan for further testing/exercises will form part of this sign off. Update 28th August 2015: OPCC’s Business Continuity plan is 80% completed. Deadline for the completion has been pushed back to end of October due to a staff vacancy requiring other members of the team to cover additional work during the recruitment phase to fill the vacancy. Update November 2015: Currently the Business Continuity Plan is 90% complete and a new timeline has been drafted. A final version of the Plan should be drafted in December 2015 and presented to the Senior Management Team. Progress has been delayed due to staff shortage within the Governance Team resulting in the Assurance Officer having to undertake additional statutory work. An appointment to the vacant role has been made and a new member of staff is expected to be in place in January 2016. Until this time the Assurance Officer will be required to continue to undertake the additional responsibilities. |  |  |  |  |  |  |  |  |  |  |  |
|  | ESTATES MANAGEMENT |  |  |  |  |  |  |  |  |  | 3 July 2014 |  |  |
|  | HIGH: 0 |  |  |  |  | MEDIUM: 0 |  |  |  |  |  | LOW: 2 |  |
|  | Low Recommendation 1.1a: Undertake a planned periodic review of the Estates Strategy to ensure it remains relevant and reflects the direction of travel. Implementation Target Date: 2015 in line with Change Programme Person Responsible: Andrew Wroe – Head of Estates Initial Management Comment: This was planned to be carried out in 2015 and will fall in-line with the change programme. Update November 2014: Still planned to undertake this in the summer of 2015. Update March 2015: Still on track for completion in the summer. Update August 2015: – Baker Tilly Follow Up Report 2015: The two actions for Estates are not scheduled to be complete until Summer 2015 but I also require C/Supt Rob Nixon’s proposals for the future of the estate before I can update the Estates Strategy. Update November 2015: Complete. Estates Strategy Update report is written and is now with Chief Officers to go through the approval process. PROPOSE CLOSE |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Low Recommendation 1.1b: Ensure there are clear links in the Estates Strategy to both the Police and Crime Plan and Leicestershire Police aims and objectives. Implementation Target Date: 2015 in line with Change Programme Person Responsible: Andrew Wroe – Head of Estates Initial Management Comment: This will be incorporated when the above review takes place. Update November 2014: Still planned to undertake this in the summer of 2015. Update March 2015: Still on track for completion in the summer. Update August 2015 – Baker Tilly Follow Up Report 2015: The two actions for Estates are not scheduled to be complete until Summer 2015 but I also require C/Supt Rob Nixon’s proposals for the future of the estate before I can update the Estates Strategy. Update November 2015: Complete. Estates Strategy Update report is written and is now with Chief Officers to go through the approval process. PROPOSE CLOSE |  |  |  |  |  |  |  |  |  |  |  |  |
|  | RISK MANAGEMENT |  |  |  |  |  |  |  |  |  | 6 January 2015 |  |  |
|  | HIGH: 0 |  |  |  |  | MEDIUM: 1 |  |  |  |  |  | LOW: 0 |  |
|  | Medium Recommendation 1.2: Force - Workshop and training for staff should include risk controls assurance. Implementation Target Date: December 2015 Person Responsible: Laura Saunders – Risk and Business Continuity Adviser Initial Management Comment: An annual workshop with the SORB members is planned for 2015; this will include risk controls assurance. Update March 2015: The annual workshop is scheduled to go ahead in the July 2015 SORB meeting. Update 26th August 2015: The annual risk identification workshop was completed with SORB members on 30th July. This interactive workshop led members through the risk assessment process. It also included an input about how ongoing monitoring of risks should include assurance mapping to gain positive assurances that controls are effective and to identify any gaps. Update November 2015: The annual workshop has been completed This interactive workshop led members through the risk assessment process. It also included an input about how ongoing monitoring of risks should include assurance mapping to gain positive assurances that controls are effective and to identify any gaps. PROPOSE CLOSE |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SEIZED AND FOUND PROPERTY (3.14/15) |  |  |  |  |  |  |  |  |  | 11 September 2014 |  |  |
|  | HIGH: 0 |  |  | MEDIUM: 1 |  |  | LOW: 0 |  |  |  |  |  |  |
|  | Medium Recommendation 1.1: As planned the Property Management Policy and Procedures should be reviewed and revised, taking into account any issues identified within this review. Given the issues identified in this review we would recommend that once the Policy and Procedures have been finalised and approved a training session is held with Property staff to ensure that they are fully conversant with requirements, especially any changes that have been made from original documents. Implementation Target Date: March 2015 Person Responsible: Insp Mark Zanker Initial Management Comment: The review of property is now well underway and the team involved are identifying opportunities to streamline processes and increase efficiency which will be relevant to the policy and procedures. Initial work on the refresh and re-write of the policy and procedures is expected to commence in November 2014 when resources within DJD Support have the capacity. Update August – Baker Tilly Follow Up Audit 2015: The policy re-write is still ongoing. Very limited availability of staff trained to write policy and competing demands of Property managers continue. Sgt 4320 Simpson (CAID Support) and Julie Treen (Property Team Leader) are tasked to finalise the re-write with a timescale for completion prior to 8th June. Update 27th August: The policy re-write is now complete and is presented in Authorised Professional Practice format, together with an up-to-date Legislative Compliance pack. The document is going through a final checking process before being sent to COT for authorisation, published / updated on internal web-site. This will be completed imminently. Any changes in practice have been subject to internal communication both within the property department and where necessary to a wider relevant audience. Update November 2015: The final checking process on the rewritten policy and procedure documents has been completed. The documents were sent to D/Supt. Castle on 2nd September for his approval and submission to COT for authorisation. A progress check will be made with D/Supt Castle on his return from annual leave on the 17th November and an update provided for the next meeting. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | FINANCIAL CONTROLS - AGRESSO SYSTEM WALKTHROUGH |  |  |  |  |  |  |  |  |  | 8th April 2015 |  |  |
|  | CONFIRMED: 46 |  | CONFIRMED with minor changes: 2 |  |  |  |  |  | NEW PROCESS: 2 |  |  |  |  |
|  | Person Responsible: Ruth Gilbert Head of Finance Baker Tilly conducted a Financial Controls audit reviewing the existing control framework in place in a number of key areas, and documenting planned changes to processes resulting from the change of Finance system from Sage to Agresso, which is planned to go live in August 2015. The audit consisted of walkthrough testing to confirm the control framework in place and was based on the documented processes from previous audits conducted, together with liaison between key staff during the review. The areas covered were: - General Ledger, - Income and Debtors, - Procurement, Creditors and Payments, and - Cash, Bank and Treasury Management. Limited control processes relating to expenses, overtime and enhanced payments have been covered however, the review focussed on the activity completed within Finance Operations and as such did not cover the whole control framework within the Payroll Department. This team utilises a separate system and there was no expectation that there would be changes to the existing processes with the introduction of Agresso. The review has not covered the controls operating at the Payroll Provider as this is a separate audit and as the processes completed by the third party did not require access to the Force Finance Systems. Budgetary control processes remain unchanged and at the time of audit the ‘Planning’ (Budgetary Invoices) and ‘Inventories’ (Assets) modules of Agresso were not part of the current phase being rolled out in Agresso. As Baker Tilly were not informed of any planned changes to the processes with the introduction of the new Finance system these areas have not been included in the coverage of their review. Update 27th August: The Finance Department are currently undergoing the changes associated with this audit therefore an update progress report will be provided at the next JARAP meeting. Update November 2015: The Agresso Financial Management System went ‘Live’ on the 1st September. Mazar’s are currently undertaking the Key Financials audit which includes testing the controls identified in the Agresso System Walkthrough. Any issues identified with the operation of the key controls will be raised in the Mazar audit reports. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | COLLABORATION – East Midlands Operational Support Services (EMOpSS) |  |  |  |  |  |  |  |  |  | May 2015 |  |  |
|  | HIGH: 0 |  |  | MEDIUM: 2 |  |  | LOW: 1 |  |  |  |  |  |  |
|  | Medium Recommendation 3.2.1 The savings associated with the other costs that will be incurred (for example, but not limited to, transport and uniform) should be explored and incorporated within the overall efficiency savings for EMOpSS. Furthermore, capital savings should be identified and explored for inclusion within the overall savings. This could potentially be significant and we would encourage the forces to explore such areas of spend for inclusion within the identified savings. Implementation Target Date: April 2016 Person Responsible: C/Supt Chris Haward Initial Management Comment: This is part of the second phase of EMOpSS once the operational model is in place. There are existing working groups for Roads, Armed, Public Order, Dogs and Specialist Policing all of which are looking at procurement, capital savings and equipment. All of these meetings have been running for several months and, again, are well minuted and evidenced. The above is also covered in the draft Business Plan for EMOpSS which will be submitted to the Strategic Management Board for sign off in May. It should also be noted that the business case sets a time frame of April 2016 to realise savings and reset the budget and we are currently 1 year ahead of schedule in recouping the operational savings from the new model. Progress Update 26th August 2015: These issues have always been part of our considerations. We have working groups and lead officers working on: - Fleet (Insp Gowler - EMOpSS) - Procurement Optimisation (Jayne Gowler - Notts) - Uniform & Equipment (Ch. Insp. Dave Lawson - EMOpSS) - Financial Analysis and Efficiency (Mick Robinson – Lincs) Current projection against actual budget for EMOpSS is that a further £2m (estimated) may be saved and the budget reset for April 2016 as per project time lines. Fleet management and change in vehicle specifications means we can now seek to purchase vehicles other than BMW X5 and 5 Series. New vehicles available from Sept include Volvo, Audi and VW. Savings in the hundreds of thousands of pounds are expected once this procurement framework opens up. The Strategic Business Case for 2015/16 has a full section on driving out efficiency and this plan is being worked through by the Senior Leadership Team and the above teams. All of this is governed through the Strategic Management Board chaired by CC Neil Rhodes. Update November 2015: The work detailed above continues to make good progress and papers for the November EMOpSS Strategic Management Board detail the financial forecasts for the year. This report states: Staff Costs – Centrally Funded (Costs in relation to the Command and Business Support element of EMOpSS and split using the Four Force funding formula) Details of the current centrally funded staff costs are shown at Appendix A. Total budget is £2,890,311 with an actual spend of £2,670,589 being projected as the outturn for the 2015/16 year. The Centrally funded staff costs are showing a projected underspend (£219 k) against the proposed project assumption cost due to the business case using an average cost based on a higher rate of police officer salary. Should the figures remain constant then the year end position would show that Leicestershire (£83k) and Lincolnshire (£81k) would receive refunds, against their salary costs whilst Northamptonshire and Nottinghamshire would require to pay further contributions in order for the centralised costs to be redistributed using the four Force funding formula. (£44k and £121k respectively) Staff Costs – ‘In Kind’ (Costs in relation to Police Officers and Support staff resources provided to EMOpSS by the individual Forces within the collaboration which are not recharged using the Funding formula, but are provided ‘in kind’ ) Details of the current position of the staff costs ‘in kind’ are shown at Appendix B. The budgeted cost is £26,919,693 with a projected spend of £24,539,977 which shows a projected underspend of £2,379,716. Again the projected underspend is due to the higher than average costs been used within the initial business case. Whilst the ‘In-kind’ costs show an underspend it was not the intention of the business case that officers and staff resources provided ‘In-kind’ would be split using the four Force funding formula but that these costs would be monitored as a ‘Cash value’ to ensure that each Force contributed the relevant resources. Currently the ‘In-kind‘ costs still show a significant under contribution from Nottinghamshire Police, using the revised funding formula set out in the business case the equivalent under contribution expressed as a ‘Cash value’ is £975.6k, which equates to around 18 PC’s. Revenue (Running) Costs (Costs agreed as the associated running costs of EMOpSS, Vehicles costs etc. Split using the Four Force Funding Formula) Within the Business Case a number of assumptions were made surrounding the EMOpSS running costs. For example, the initial business case requested budgeted costs for ‘operational’ departments from each Force however these costings did not take into account those budgets that individual Forces have as centralised costs e.g. ‘fuel’ costs. The disparity between Forces budgets was clearly significant: - Lincolnshire £230k - Northamptonshire £233k - Leicestershire £1.015k - Nottinghamshire £1,877k Work has been carried out to first identify these support/organisational costs and secondly to agree a position whereby these could be reported upon. Agreement has now been reached between the Finance SPOCs from each Force as to what should be included to form the basic ‘running costs’ of EMOpSS. These actual running costs will be recharged at the year-end using the four Force funding formula. Budget Settings Process 2016/17 – Initial meetings have been scheduled for the setting of the 2016/17 budget including the request to reduce budgets by 5% and 10% along with a three year budget plan for the PCC Board (January 2016). |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Low Recommendation 3.2.1 We would challenge if £50,000 is sufficient to cover the IT implementation, but accept that there is substantial funds available to fund any additional costs. However, it would be beneficial to monitor and report the actual costs associated with ICT implementation, to not only monitor the planned savings for EMOpSS but also to inform future Business Cases Implementation Target Date: April 2015-April 2016 Person Responsible: ACC Torr / C/Supt Haward Initial Management Comment: We recognised that £50k was insufficient but the audit report fails to recognise the innovation fund bids that had been submitted to counter this – one for ANPR and one for Agile Working. The former has not been approved but the latter has given £650k to address the issue across EMOpSS. The bid was available at the time of the audit, albeit the outcome was not known at that time. A working group led by ACC Torr is now driving implementation of this. Audit Comment Management comment is noted and agreed. Progress Update 26th August 2015: There has been minimal ICT set up costs to date – the main purchase we are likely to need is approx. £8K to cover new DMS licences for Leicestershire Officers. Primary development of ICT is through the innovation fund and contract for this has been awarded to HCL. Progress underway and all costs for this are managed through the Project Manager Steve Handley and ACC Simon Torr in Nottinghamshire. Update November 2015: Innovation fund project continues – contract awarded to HCL. Roll out of first phase expected early in 2016. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Medium Recommendation 3.5 Given the current levels of collaboration and the intentions to increase collaboration further, we would encourage the Regional Forces to review the oversight and monitoring arrangements in place to ensure that are Forces remain comfortable with how collaborative projects are being monitored and managed, or whether there are any benefits in expanding the existing Regional Team to provide this current significant demand. Implementation Target Date: Ongoing Person Responsible: East Midlands Regional Forces – C/Supt Haward Initial Management Comment: To be considered Update November 2015: EMOpSS is governed through the Strategic Management Board chaired by the SRO CC Neil Rhodes. ACCs from each force attend this and the SMB provides an update report to the regional collaboration board each quarter. The SMB has good oversight and scrutiny and has seen the realisation of over £5m in savings with potential for further £2m + whilst performance has been consistently above business case projections. PROPOSE CLOSE |  |  |  |  |  |  |  |  |  |  |  |  |
|  | PERFORMANCE |  |  |  |  |  |  |  |  |  |  |  | Aug 2015 |
|  | HIGH: 0 |  |  | MEDIUM: 0 |  |  | LOW: 1 |  |  |  |  |  |  |
|  | Low Recommendation 1.1 Where there are performance exceptions highlighted in the Recorded Crime reports to the Force Executive Group, there should be a clear record in the meeting minutes to evidence the challenges and scrutiny undertaken by the Senior members of the Force. Implementation Target Date: August 2015 Person Responsible: C/Supt Steph Pandit Initial Management Comment: This recommendation is accepted and will be addressed through the review of force performance and will be addressed where necessary by the Chair of the meeting through the minutes - C/Supt Steph Pandit – Head of Corporate Services as business lead on Performance. Update 26th August 2015: This work is approaching completion and proposals will also support the current regional work stream incorporating a coherent approach to recording performance within regional teams (e.g. EMSOU & EMOpSS). It is anticipated that once agreed, the new performance framework will be utilised at the Force Performance Group meeting on the 13th October 2015. Update November 2015: Action complete - A new approach to monitoring force performance, based on HIMIC PEEL inspection pillars was approved at the Force Executive Group on 9th October, 2015 for implementation at the Force Performance Delivery Group scheduled for 17th November, 2015. Where exceptions in performance are identified measures are in place to record clearly through minutes/actions thereby evidencing scrutiny and where appropriate challenge by senior and chief officers of the force – C/Supt Steph Pandit. PROPOSE CLOSE |  |  |  |  |  |  |  |  |  |  |  |  |
|  | End |  |  |  |  |  |  |  |  |  |  |  |  |

MAZARS AUDITS

Please note Mazars priority grade their recommendations into the following:

- (Fundamental)

- (Significant)

- (Housekeeping)

| Status | Internal Audit Report |  |  |  |  | Audit Report Date |
| --- | --- | --- | --- | --- | --- | --- |
|  | FIREARMS LICENSING |  |  |  |  | August 2015 |
|  | FUNDAMENTAL: 0 |  | SIGNIFICANT: 2 |  |  | HOUSEKEEPING: 1 |
|  | Housekeeping Recommendation 4.1 Procedure notes should be reviewed, appropriately approved and communicated to all relevant staff on a regular basis. Implementation Target Date: September/October 2015 Person Responsible: Nigel Rixon - Firearms Licensing Manager Initial Management Response: As stated the up dated version of the document has yet to be ‘signed off’. Mr Rixon is expected to return as Manager in a police staff role late in August 2015 when it is anticipated the process will be completed. Update November 2015: Firearms Policy reviewed and approved by C/Insp Walls Sept 2015. All policy changes notified to staff at time of change or if relevant at quarterly meetings. Recommendations are now completed and would withstand scrutiny. PROPOSE CLOSE |  |  |  |  |  |
|  | Significant Recommendation 4.3 All certificates should be approved by the appropriate party with delegated authority and a segregation of duties should occur between the visit to the applicant and the approval of the certificate. Implementation Target Date: September/October 2015 Person Responsible: Nigel Rixon - Firearms Licensing Manager & HR Recruitment Initial Management Response: We acknowledge the recommendation and the importance in carrying out this task. Staff have been reminded that they are required to undertake and record this task and the potential ramifications to the force and wider public. A capacity issue has already been identified and the force is currently recruiting an additional supervisor to provide improved capability and capacity. Update November 2015: Segregation of duties now takes place. Resilience for this is now structured in with a new Supervisor in post and C/Insp Walls being given delegated authority. Recommendations are now completed and would withstand scrutiny. PROPOSE CLOSE |  |  |  |  |  |
|  | Significant Recommendation 4.4 In light of the ‘fast-tracked’ applications, the procedures supporting the home security visits required prior to approval of a certificate should be reviewed, updated if necessary and appropriately approved. Implementation Target Date: August/September 2015 Person Responsible: Nigel Rixon - Firearms Licensing Manager Initial Management Response: The practice of ‘Fast Tracking’ is only utilised where the applicant is rated as low risk. There are procedures in place (and were at the time of the audit) to ensure that Enquiry officers are aware of expiry dates and whether certificate is granted or not, if a visit cannot be carried out prior to expiry of the certificate, then holder is requested to lodge weapons (if indeed he holds any). All fast tracked certificates are signed as ‘provisional’ only and if there is any cause for concern at the time of the visit the certificate is not handed over however it is accepted that the practice of ‘fast tracking’ has not been covered in the current Policy Document and this is to be reviewed with Licensing Manager, Mr Rixon upon his return and to be included in the newest version of this document which is currently under review. Update November 2015: Fast tracking now documented in Force Policy and approved by C/Insp Sian Walls PROPOSE CLOSE |  |  |  |  |  |
|  | RISK MANAGEMENT |  |  | October 2015 |  |  |
|  | FUNDAMENTAL: 0 | SIGNIFICANT: 0 |  |  | HOUSEKEEPING: 3 |  |
|  | Housekeeping Recommendation 4.1 Consideration should be given to formally cascading the risk management training down to staff within the individual Directorates. This could take the form of training sessions or availability of the training material on the Force intranet. Awareness of this training and availability of the most recent Risk Management Procedure should be highlighted to staff across the Force. Implementation Target Date: March 2016 Person Responsible: Laura Saunders Initial Management Response 29th October 2015: Training materials covering risk identification and the risk assessment process will be included within the intranet pages of the Risk Management Unit. Separate risk identification sessions will be delivered to the individual directorates via the SMT structures. The training materials and current risk management procedure will be highlighted to staff via the latest news pages of the intranet. |  |  |  |  |  |
|  | Housekeeping Recommendation 4.2 In line with the Risk Management Procedure, risk should be evidenced as a standing agenda item at each Senior Management Team meeting. Implementation Target Date: December 2015 Person Responsible: Laura Saunders Initial Management Response 29th October 2015: The Risk Management Procedure clearly states that risk should be included as a standing agenda item at each SMT Meeting. We will ensure that this is explicit within the individual agendas moving forwards. |  |  |  |  |  |
|  | Housekeeping Recommendation 4.3 Periodic exercises should be undertaken to provide assurance that all service areas within the Force Directorates are actively identifying risks from a formal scanning process and reporting these as a result. If the gap analysis highlights any service area which does not have any current risks (being departmental or strategic) then confirmation with the Head of the service area should be sought to confirm there are no current identified risks within their environment. Implementation Target Date: March 2016 Person Responsible: Laura Saunders Initial Management Response 29th October 2015: Work will be undertaken with all service areas to ensure they are actively scanning for and identifying risks. The results of this will be shared with the directorate risk SPOCs. Where service areas have a nil return of risks (departmental or strategic), assurance will be sought from them that there are no current identified risks within their environment. Assurance will also be gained through dip sampling and monitoring through SORB, JARAP and the revised Performance Development Group (PDG). |  |  |  |  |  |
|  | End |  |  |  |  |  |